BIOMETRY & EPIDEMIOLOGY

135 Cannon Street. Suite 303

PO Box 250835

Charleston, SC 29425

Phone (843) 876-1100

Fax (843) 876-1126

September 29, 2003

Ms. Nancy B. Pillar

Procurement and Grants Office

2920 Brandywine Road, Suite 3003

Grants Management, CDC

Atlanta, GA 30341-5504

Dear Ms. Pillar,

Attached with this cover letter is the revised work plan of the South Carolina Traumatic Brain Injury Follow-up Registry (SCTBIFR) that addresses the terms and conditions of the grant award noted on the July 29, 2003 document.  The report includes a revised budget geared towards activities that are highlighted in the terms and conditions of the grant award.  We are confident that the specific issues noted by the Special Emphasis Panel are fully covered in this report.  Hope to hear from you soon.

Sincerely,

Anbesaw W. Selassie, DrPH

Principal Investigator, SCTBIFR

Department of Biometry and Epidemiology

Medical University of South Carolina

Charleston, SC 29425

cc:  Mr. Jim Enders

Team Leader

Program Development and Surveillance Team

Division of Injury and Disability Outcomes and Programs

NCIPC, CDC

Table of Contents

Content						          Page

1.   Executive Summary

2.   Revised Year 02 Objectives							 1

- Data Dissemination and Data Sharing Plan			  	 	 7

- Program Reorganization and Delegation of Responsibilities 			11

- Specific Plan to Implement the Recommendation of the EAC			15

- Programmatic Shifts and Potential Implications					18

- Budget Update and Justification							20

Tables

Table 1.  Proposed Publication Plan using the first 2,104 participants			12

Table 2.  Changes in Statistical Power by proposed and recommended sample sizes	19

Figures

Figure 1.  Observed and projected number of interviews				18

Appendices

Appendix A:  Final Report of the Qualitative Background Study

Appendix B:  The SC Integrated Data System at ORS

#### Year 02 Revised Program Plan

Executive Summary

The South Carolina Traumatic Brain Injury Follow-up Registry (SCTBIFR) revised the Year 02 objectives to address the Division of Injury and Disability Outcomes and Programs, National Center for Injury Prevention and Control, CDC requirements for implementing the recommendation of SEP as outlined on the July 29, 2003, award requirement.  SCTBIFR is pleased to report significant progress towards achieving these requirements.

The responses included in this document address the completion of, a) manuscript on death after discharge, b) manuscript on the operations of the study, c) the data codebook, d) a web-based monograph, and e) the manual of operations.  The project is confident to complete these important tasks by the dates stated in the revised objectives.  The revised objectives are measurable, time-specific, and incorporate the proposed methods of operations. The work plan also includes the personnel responsible for completing each of the objectives.

The staff and investigators of SCTBIFR have worked hard to collect follow-up data of demonstrable quality.  The success attained reflects the joint input of the CDC, the state partners, the SC TBI leadership Council, and the remarkable stewardship of the Medical University of South Carolina.  This result is also the testament of the strong partnership the SC organizations have to collaboratively work with the CDC.  Such genuine collaboration has been the hallmark of all of the South Carolina’s CDC-NCIPC funded projects since 1992.

The proposed work plan includes the delegated responsibilities of the reorganized team along with a revised, simplified organizational structure.  The teams are reorganized by function and each team has a delegated team leader to oversee the activities.  The SCTBIFR steering committee members and the investigators believe that this reorganization is timely in light of the transition the project needs to make from data collection to data dissemination.

The SCTBIFR is pleased to receive the expert input of the External Advisory Committee (EAC).  The committee has made invaluable suggestions and comments that are critical to maximize the usefulness of the data.  This revised work plan incorporates methods and plans to undertake each of the highly appropriate and very useful recommendations.  Cognizant of these important contributions, the project designated one of the co-investigators to be in charge of overseeing the implementation of the recommendations of the EAC.  We are also pleased to report that three conference calls, each 90-minute long, have been scheduled.  These conferences will take place on November 12, 2003, March 10, 2004, and July 21, 2004.

This report outlines the project’s data dissemination and data sharing plan.  This plan is based on the principle of fairness, legitimacy, and professional ethics.  The plan allows unhampered access to all investigators, CDC advisors, and advisory committee members within the defined federal guidelines and established methods of accessing the data until data fall in public domain.  As a publicly funded research project, SCTBIFR promotes the use of the final research data by all researchers and scientists to expedite the translation of research into meaningful practices to improve the lives of people with TBI.

### I.  Revised Year 02 objectives

          - By September 30, 2003, SCTBIFR will have completed Phase II (Qualitative background research) of Violence, Abuse, and Neglect (VAN) study and phased out Phase III (follow-back interview) of VAN. SCTBIFR will cease all preparatory activities regarding Phase III of the VAN sub-project.  Resources and programmatic foci will be diverted to accomplishing the core project’s priority area of dissemination and data quality assessment.  The qualitative background research (Phase II) has been completed. The final report of the qualitative background study is attached with this report (Appendix A).  Ms. Audrey Richards and Dr. Pat Sample compiled this report.

          - By September 30, 2003, SCTBIFR will have discontinued the prison subproject. The prison subproject will be discontinued effective September 30, 2003 in accordance with the SEP recommendation.  Employees of the project slated to work on this project are already notified about this change. The MUSC IRB and the Department of Correction employees involved in the planning stages of the study will soon be notified that the study will not be conducted as part of SCTBIFR.  However, the project will continue requesting quarterly data on the inmate stock population census data for tracking of the whereabouts of participants who completed first and second interviews but could not be found for the subsequent interviews.  Dr. Elisabeth Pickelsimer will be responsible for redirecting of the resource allocated to prison subproject and communicating about the discontinuation of the subprojects with all the parties involved.

          - By November 30, 2003, SCTBIFR will have submitted the continuation IRB protocol to the CDC.  The project’s current year IRB approved protocol expires on February 12, 2004. Renewal applications will be submitted at least six weeks in advance of the expiry date.  The project has consistently kept the submission of the renewal application before the expiry date.  Dr. Elisabeth Pickelsimer will be responsible to ensure that the renewal applications are completed and submitted by the due date.

          - By November 30, 2003, SCTBIFR will have submitted a manuscript entitled, ‘Population-based outcome surveillance of persons hospitalized with Traumatic Brain Injury: Operations of the South Carolina Traumatic Brain Injury Follow-up Registry’ to the Archives of Physical Medicine and Rehabilitation.  The project will develop this manuscript to address the operational components of the follow-up system and provide information that could be pivotal for entities that plan to develop a population-based follow-up system.  The impetus for this manuscript was borne out of the many questions the project received from various entities regarding how to develop a population-based follow-up registry.  The specific methods involved for developing this manuscript entails, a) organizing the team of authors in accordance with the project guideline, b) identifying the appropriate journal, c) reviewing the literature, d) compiling the components of the SCTBIFR, and e) writing and reviewing the content.  Dr. Elisabeth Pickelsimer is the person responsible to accomplish this manuscript submission.

          - By November 30, 2003, SCTBIFR will have submitted a manuscript entitled, ‘Patterns of alcohol use 1 year after TBI: A population-based epidemiological study’ to the Journal of the American Journal of Psychiatry. In accordance with the recommendation of the external advisory committee, SCTBIFR will address the priority area of alcohol use among persons with TBI for publication in a peer-reviewed journal.   Previous studies of alcohol use in individuals with TBI have examined clinical samples, such as patients from rehabilitation programs.  This manuscript will present patterns of alcohol use one year after TBI in a population-based sample.  In this paper, alcohol use in the month prior to interview will be classified according to categories from the Quantity-Frequency-Variability Index (QVFI).  Adolescents (age 15-17 years) will be excluded.  The specific methods involved in this manuscript development include, a) organizing the authors’ team, b) conducting literature review, c) determining the distribution of alcohol use as “heavy”, “moderate”, and “light/abstainers”, d) determining confounders and explanatory variables, f) conducting the analysis, and g) writing the manuscript.  Dr. Michael Horner is the lead author and the responsible person to oversee the accomplishment of this objective.

          - By December 31, 2003, SCTBIFR will have submitted a manuscript entitled, ‘A population-based assessment of factors associated with death within 1 year after discharge with TBI’ to the Medical Care Journal.  SCTBIFR data indicate that 10.5% of the persons contacted for interview were deceased within 1 year after discharge from acute care facilities.  This rate of death is about 3 times higher than what is reported for other trauma patients or 4.5 times greater than the age-race-gender adjusted mortality rate of the US population.  There is clear indication that these persons are dying due to the lingering effect of the TBI or TBI could have accelerated the morbid effect of pre-existing chronic health conditions.  The specific methods of completing this manuscript involve, a) organizing the authors’ team, b) conducting the literature review, c) identifying the deaths from the follow-up database, d) confirming that these deaths have indeed occurred by cross-checking with the SSA web-based mortality listing, e) acquiring cause of death information from the multiple causes of death data, f) conducting the analysis, and g) writing the manuscript.  Dr. Anbesaw W. Selassie is the lead author for this manuscript and the person responsible to oversee the accomplishment of this objective.

          - By December 31, 2003, SCTBIFR will have completed the data codebook.  The data codebook is a critical document to promote information dissemination through scientific, peer-reviewed manuscripts.  This document will allow the project co-investigators and other researchers to identify the variables they would like to use for the various domains of research interest.  It will include three sets of variables: Part A: Core variables from the discharge data set, Part B: Extended variables from medical record review, and Part C: Interview variables.  The interview variables will include frequencies of the responses for each year of interview.  The methods of completing the codebook involve, a) organizing the research team and delegating specific tasks, b) collating the components of the document, and c) completing the frequencies.  Periodic progress in the codebook development will be discussed at the monthly investigators’ meeting.  The person responsible to oversee the accomplishment this objective is Dr. Anbesaw W. Selassie.

          - By December 31, 2003, SCTBIFR will have completed acquiring cause of death information of at least 350 individuals with TBI who died within the first year and 50 individuals who died within second year after discharge from acute care facilities.  SCTBIFR will acquire cause of death information of individuals randomly selected to participate in the follow-up study but died within 1 after discharge from acute care facilities with TBI.  These individuals are permanently identified through mail returns, and family members’ responses, or the SSA web-based listing of deaths in the US.  The lists of names of the persons reported as deceased are counterchecked with the SC DHEC Vital Records database to authenticate the deaths. Progressive file merging with the Multiple Cause of Death Data file is currently in place to identify the underlying and contributing cause of death, place and manner of death, and date of death.  To date, the records of 260 persons who died in 1999, 2000, and 2001 have been merged.  Mr. Wes Gravelle will be responsible for the accomplishment of this objective.

          - By January 31, 2004, SCTBIFR will have submitted a manuscript entitled, ‘The unmet service needs of persons with TBI: A population-based epidemiological assessment 1 year after discharge with TBI’ to the Achieves of Physical Medicine and Rehabilitation. To maximize the usefulness of the data for policy development and scientific impact, SCTBIFR will exert maximum effort to identify the unmet needs of persons with TBI.  This study will attempt to express unmet needs against the background of recognized functional, neuropsychological, and social problems.  Both qualitative and quantitative analytic techniques will be incorporated to report the findings.   The specific methods of completing this manuscript involve, a) organizing the authors’ team, b) conducting the literature review, c) identifying the key areas of reported deficits and problems, d) cross-tabulating the recognized deficits and problems by the reported service needs, e) clustering qualitative responses into themes, f) conducting the analysis, and g) writing the manuscript.  Dr. Elisabeth Pickelsimer will be the lead author of this manuscript and she will oversee the accomplishment of this objective.

          - By March 31, 2004, SCTBIFR will have submitted a manuscript entitled, ‘The major outcomes of TBI 1 year after discharge from acute care facilities’ to the Journal of Trauma.  The main objective of this manuscript is to provide the salient outcomes of TBI as observed in this population-based study.  The analysis will examine the proportion of persons with TBI who reported significant deficits in cognition, activities of daily living/instrumental activities of daily living (ADL/IADL), poor composite general health, substance abuse, and lower satisfaction with life (SWL).  There will be effort to identify the factors that are strongly associated with lower SWL, which will be treated as the main response variable.  The specific methods of completing this manuscript involve, a) organizing the authors’ team, b) conducting literature review, c) identifying the major areas of reported deficits and problems, d) conducting the analysis, and e) writing the manuscript.  Dr. Anbesaw Selassie will be the lead author and the person responsible to oversee the accomplishment of this objective.

          - By March 31, 2004, SCTBIFR will have completed data quality assessment to validate inter-and intra-interviewer consistency.  In compliance with the SEP recommendation, we will explore the prospect of assessing inter- and intra-interviewer agreement in consultation with the External Advisory Committee and the CDC.  In addition to assessing internal consistency and reliability of the related responses, the project’s current method of assessing data quality includes monitoring up to five randomly selected interviews monthly by the lead interviewer. The lead interviewer gives feedback to the interviewers at the end of the attended interviews.  The lead interviewer uses the ‘interview administration manual as the ’benchmark for assessing the quality of the interviews.  The project chose this approach of assessing data quality due to the protracted time it takes to administer the interviews and the slow response time of many of the participants.  While the assessment of both inter- and intra-rater consistency by repeated administration of the survey tool within a short time interval are important steps, the practicality of conducting this evaluation in our cohort has yet to be explored.  To this effect, we are proposing to conduct this evaluation in the following manner.  A) The project will develop an abridged version of the tool for re-interviews by retaining items of the questionnaire that are apt to measurement or response errors.  B) Two sets of 20 systematically sampled participants will be selected (total n=40).  The first set of 20 participants will be re-interviewed within a period of two weeks after the standard interview using the abridged tool by the same interviewer who conducted the standard interview, i.e., interviewer A on subject i1 at t1 vs. interviewer A on subject i1 at t2.  The second set of 20 participants will be re-interviewed in the same method as the first 20 but the interviewers will be different, i.e., interviewer A on subject i2 at t1 vs. interviewer B on subject i2 at t2.  The former is expected to yield the intra-interviewer reliability and the latter the inter-interviewer reliability assuming the interviewees provided consistent report in their responses at t1 and t2.  The CDC technical advisor and the external advisory committee members will review this method and appropriate modification will be included before implementation.  This will be the first agenda item that will be discussed on the November 12, 2003 conference call with the EAC and the CDC.  Drs. Paulo Guimaraes and Pam Ferguson and will be responsible for the execution of this objective after approval of the method by the EAC and the CDC.

          - By April 30, 2004, SCTBIFR will have evaluated the quality of the data addressing internal consistency, response completeness, and generated a report.  SCTBIFR will assess the quality of the data acquired through UB-92 billing report, medical record review, and the interview process.  Data acquired from UB-92 billing report will be evaluated for predictive value positive (PVP) according to the CDC TBI surveillance guideline.  Data from the survey tool will be evaluated for internal consistency with Cronbach’s alpha by comparing of variables that measure the same effect. This assessment will continue to be part of the ongoing method of data quality assessment. Dr. Pam Ferguson will be responsible to ensure for the timely execution of this objective.

          - By May 31, 2004, the SCTBIFR will have submitted a manuscript entitled, ‘General Health Status of persons with TBI 1 year after discharge from acute care facilities’ to the Journal of Quality of Life Research.  The main objective of this manuscript is to evaluate the general health status among persons with TBI 1 year after discharge from acute care facilities.  The analysis will identify the proportion of persons with TBI who reported poor/fair, good, and excellent general health.  This study will assess the various subscales of general health and will incorporate log linear modeling to identify predictors of poor/fair general health.   The specific methods of completing this manuscript involve, a) organizing the authors’ team, b) conducting literature review, c) determining the distribution of the composite and subscales of general health scores, d) conducting the analysis, and e) writing the manuscript.  Dr. Jean Langlois will be the lead author of this manuscript.

          - By May 31, 2004, SCTBIFR will have developed web-based portable data files (PDF) on the 2,104 persons with TBI who completed year-one interviews.  SCTBIFR will develop a dynamic website to post PDF files that shows weighted frequencies of the salient findings of TBI outcomes.  The main purpose of this effort is to rapidly disseminate basic, unadjusted descriptive data to inform the general public, TBI researchers, service providers, and policy makers.  The methods of posting the web-based PDF files will include, a) introductory statements on the project, b) the study design and operational components of the follow-up system, and c) one-way and two-way frequencies on selected outcome domains.  When two-way tables are formulated, they will be cross-tabulated by age group categorized into 5 categories (15-24, 25-44, 45-64, 65-74, 75 and older).  Hard copy templates will be shared with the CDC, project investigators, Steering Committee and External Advisory Group members prior to posting the results. When the data are complete and risk factor information is known, more specific descriptive results can be added to the website. The project has formed a committee to lead this effort.  The person in charge of this effort is Dr. Melissa McCarthy.

          - By June 30, 2004, the project will have completed the Manual of Operations.  The project will revise the partially completed Manual of Operations to provide detailed procedural account of the activities of the follow-up registry.  The manual of operations will have four volumes.  Volume I includes detailed information on study design and development, methods, and operations.  Volume II includes questionnaire source and the survey tool.  Volume III includes the questionnaire administration manual. Volume IV includes interviewer-training manual.  These volumes will provide detailed information on all documentations of decisions and actions taken.  The main purpose of this document is to share the lessons learned about the development and operations of a population-based TBI follow-up registry.  The methods of developing this manual will include, a) forming a task force comprised of the investigators and employees of the project, b) reviewing the documents that have been organized to date, c) delegating specific tasks, d) conducting a meeting to assess the progress, and e) compiling the final manual.  The person in charge for this committee and effort is Dr. Pam Ferguson.

          - By June 30, 2004, SCTBIFR will have completed preliminary analysis on models that predict SSI/SSDI beneficiary status after TBI.  The project will conduct methodical steps to determine the proportion of persons with TBI that have been awarded SSI/SSDI after being treated and released from the ED or admitted and discharged from the hospital from January 1, 1996, through December 31, 2002 in SC.  The method involved in this empirical evaluation includes, a) identifying persons age 16-64 who sustained TBI during the aforementioned span of time from the SC TBI surveillance database that includes both ED and hospital discharge, b) build a unified database from the two data sources that includes extended data elements, c) appending SSN, unduplicating repeat episodes for the same event, and excluding deaths through the collaborative work of ORS, d) merging the data with SSA master file and flag observations that have qualified for SSI/SSDI, and e) develop a predictive model and/or algorithm to determine the factors that explain SSI/SSDI assistance.  Drs. Paulo Guimaraes, Robert Turner, and Anbesaw Selassie will share joint responsibility for the execution of this objective.

          - By July 21, 2004, SCTBIFR will have conducted the third and final conference call for the fiscal year with the External Advisory Committee (EAC) members to discuss essential topics of interest to the project. SCTBIFR will maximize its effort to acquire expert opinion from the members of the EAC on issues that are critical to the conduct of the study and maximize scientific impact through the dissemination of the findings. The format of the conference call will be a 90-minute discussion moderated by Dr. John Corrigan on the following dates. First conference call, Wednesday, November 12, 2003; Second conference call, March 10, 2004; Third conference call on Wednesday, July 21, 2004.  Each conference call will be preceded with a progress report and an outline of 2 to 3 issues that need the input of the EAC.  The SCTBIFR investigators’ committee will identify important issues during their monthly conference calls.  Dr. Michael Horner and Mr. Wes Gravelle will be responsible to develop discussion topics and ensure all pertinent materials are distributed at least two weeks before the conference dates.

          - By July 31, 2004, SCTBIFR will have assessed epilepsy and seizure disorders (ESDs) on 2,403 persons with TBI whose discharge diagnosis included these conditions.  SCTBIFR will review medical records of persons with TBI whose discharge diagnosis included 345.0-345.9 or 780.39.  This review also includes the medical records of SCTBIFR participants who reported ESD before or after TBI.  Amendment to the current CDC IRB is in progress to allow us to link the medical records of SCTBIFR participants who affirmed experiencing ESDs before or after their TBIs.  The method of acquiring additional information through medical record reviews includes, a) identifying the medical records of those who affirmed ESDs, b) providing the list of names, medical record numbers, and hospital identifiers, along with demographical information to the SC DHEC Division of Injury and Violence for the charts to be pulled and reviewed by the abstraction team, c) analyzing the findings, and d) generating summary report on the findings.  Dr. Pam Ferguson will be responsible to oversee the accomplishment of this objective.

          - By July 31, 2004, SCTBIFR will have completed 1,575 second interviews, and 774 third interviews.  The project will continue to exert maximum effort to retain the cohort that completed first interview and conduct only second and third year interviews.  SCTBIFR ceased recruiting and interviewing new participants effective August 1, 2003 in accordance with the SEP recommendation. During this second year, SCTBIFR will strive to achieve the targeted number of second and third interviews and reduce attritions to less than 20%. To this effect, the project included supplemental work plan to the ORS subcontract to assist in the tracking of participants who completed first or second interviews but could not be located at their previous addresses for the remaining interviews.  ORS will conduct searches across their integrated data system (Appendix B) to locate these individuals. Based on the number of completed interviews by July 31, 2003, SCTBIFR will complete 352 second and 449 third interviews, total 801 interviews.  The methods involved to achieve these interviews entail, a) conducting active tracking of participants who completed first and second interviews in collaboration with ORS, b) retaining the trained and experienced interviewers, c) scheduling and conducting the interviews at hours of the day that are likely to yield interviews, such as weekends and evening hours.  The person in charge of overseeing these activities is Dr. Elisabeth Pickelsimer.

          - By July 31, 2004, SCTBIFR will have presented in at least at two national conferences addressing the findings of the study.  As part of the data dissemination effort, the project encourages presentations by the investigators at professional conferences to disseminate the findings of the study.  However, due to the limited amount of travel money in the current budget, there will be a coordinated effort to pool these presentations.  Topics to be presented will be discussed at the investigators’ monthly conference calls and the outline of the presentations or hard copies of slides will be distributed via emails.  Dr. Melissa McCarthy will oversee this objective and ensure these presentations meet the data dissemination plan of SCTBIFR.

###### II.  Data dissemination and data sharing plan

Dissemination of project findings through various venues is an important component of SCTBIFR. The project has been encouraging all investigators, staff, and the CDC Technical Advisor to pursue research publications in accordance with the suggested set of rules by the International Council of Medical Journal Editors and the SC Data Oversight Council.  Until data collection is completed, cleaned, de-identified, weighted, and salient findings are reported, data will be confined at the project headquarters.  All project investigators, staff, and the CDC Technical Advisor will have unhampered access to the database through the Biostatistics and Data Management (BDM) team as stated on page 9 under the functions of the BDM team.  The purpose of confining the data for a limited time is to provide the investigators who worked hard to collect the data the benefit from their investment of time and effort by allowing them to publish first.  In due process, the project encourages outside researchers with established TBI expertise to work with the investigators.  The members of the external advisory committee are potential sources of such expert input.  Findings will be disseminated in peer-reviewed journals, abstracts, scientific sessions, conferences, and web-based monographs as deemed appropriate. Additionally, in an effort to impact changes in public policy and service delivery in South Carolina, summaries of SCTBIFR findings will be provided to state agencies.

The SCTBIFR longitudinal data are unique data that cannot be readily replicated.  Protracted hours of hard work, effort, and public funding has made it possible to collect and organize the data.  Cognizant of this uniqueness, the project proposes to release interim findings through the web-based monograph and scientific publications with the participation of the CDC and the External Advisory Committee.  To promote data dissemination through web-based monograph, the project subcontracted with Johns Hopkins University.  Dr. Melissa McCarthy is the PI of this effort at Johns Hopkins.  The dissemination team, led by Dr. McCarthy, has already laid out the monograph plan.  The part-time Webmaster will soon be included in the support team to work with Dr. McCarthy.  The members of the data dissemination are listed on page 11.

After data collection is completed on July 31, 2004, the project will divert all resources and expertise to the data organization and documentation phase that includes, a) data cleaning and de-identifying, b) weighting of annualized and cumulative participant interviews, c) updating the data codebook with the second and third interviews, d) generating summary tables and charts, and e) preparing manuscripts on the main findings.  The public use of the final research data will follow after the aforementioned steps are completed and the major findings are accepted for publication.

As a publicly funded research project, SCTBIFR promotes the use of the final research data by all scientists and researchers to expedite the translation of research into meaningful practices to improve the lives of people with TBI.  For the first and continuing use of the research data, the project limits authorship to those who collected the data and discharged duties that assisted in the conduct of the study.  These include investigators, steering committee members, external advisory committee members, and CDC advisors. SCTBIFR recognizes that these individuals have a legitimate interest in benefiting from their investment of time and effort.  However, this only pertains to the first and continuing use but not prolonged exclusive use of the research data.

The PI of the project will ensure the progress towards successful submission of the manuscript through periodic assessment of progress on the papers.  To achieve this goal, the PI will seek assistance and counsel from Dr. Melissa McCarthy, the lead investigator in charge of summary data dissemination.  The designated lead authors on a topic areas will be accountable to submit the papers within the set timeline.  Table 1 on page 12-13, presents list of manuscript topics, potential coauthors, and journals. The lead authors listed are SCTBIFR investigators who either asked to work on the topics or were invited by the PI to be lead authors based on their expertise and interest.  However, lead authors could invite other researchers that are not affiliated with SCTBIFR to partake in the manuscript development should such inclusions become critical.  The programmer/data analyst, the project coordinator/data manager, the PI, and the co-investigator for statistical evaluation will be responsible to conduct the analysis as specified by the investigators.  The project established the following support teams to facilitate and expedite the publication and data dissemination activities

#### Support Teams for Publication and Data Dissemination Activities

The project organized two teams to assist on-site and off-site investigators to efficiently use the data collected without compromising data integrity, confidentiality, and confinement until data are organized for public domain use.  Each team has specific responsibilities to ensure data are customized and analyzed according to the needs of the researchers.  The specific tasks of the two teams are as follows.

- Quality Assurance and Data Integrity (QADI) Team:  This activity is conducted by the QADI team, which is responsible for, 1) assuring the quality of the data through an established process of periodic evaluation of internal consistency, logic and edit checks, re-abstraction of a sample of records reviewed, and monitoring a sample of the interview; 2) ascertaining data integrity and security in accordance with a) the SC Data Oversight Council policies and procedures, b) the OMB Circular A-110, which addresses data confinement and protection from FOIA until data fall in public domain, and c) procedures to maintain safety and security of data from hackers, viruses, and environmental hazards (fire, flooding, tornado, etc).  The members of the team are as follows.

- Anbesaw Selassie, DrPH, Team Leader

- Wes Gravelle, MPH

- Lou-Ann Carter, MS, Director of DIVP, SC DHEC

- Linda Veldheer, PhD, Director of HASCI Division, DDSN

- Ernest McCutcheon, MD, MPH, Steering Committee Chair and Consultant

- John Woods, PhD, USC School of Public Health

- Elisabeth Pickelsimer, DA

- Pam Ferguson, PhD

- Paulo Guimaraes, PhD

- Biostatistics and Data Management (BDM) Team:  The primary purpose of this team is to combine data into a single repository and customize the data for the specific research interest of the investigators.  There are three interdependent but functionally different data sets that could be merged as needed.  These are, a) Hospital Discharge Data Set (HDDS) that has the core surveillance variables including diagnosis, length of stay, discharge disposition, acute care charge, e-code, and demographics; b) Medical Record Abstraction (MRA) that provides the extended data elements pertaining to severity, clinical narratives, imaging, and etiological information such as alcohol involvement; c) Interview Data Set (IDS) that has extensive list of variables on post discharge status.  The unifying variable, CASEID, is the unique identifier assigned to each observation for all of the subjects randomly selected to participate in the follow-up study.  The BDM team will be the operational conduit for data analysis according to the following format.

  - Investigators define the research outline, the targeted study group, the driving hypothesis, and the variables needed for the analysis along with categorization of continuous variables pro re nata, preferred scoring scheme, and the level(s) of the dependent variable.  Investigators are expected to use the survey questionnaire and the data codebook for this purpose.

  - The PI and the BDM Team Leader go over the request with the investigators prior to delegating the data customization process.

- In collaboration with the database manager, the programmer and data analyst will create a customized data set and will provide both the SAS log and output from Proc Content and summary statistics will be provided to the investigators for the investigators’ approval.  The summary statistics will at least include distribution of basic demographics, test of normality for continuous variables, and rates of missingness.

- Investigators will write the SAS data steps and analysis procedures and send them to the programmer and data analyst.  Such programs could be written in SAS or SPSS.  If the investigators want their data steps and analysis programs to be written by the programmer and data analyst, they can do so by providing the details of the analysis plan in plain text.

- Analysis will pursue in accordance with the analytic template of the investigators.  In due process, each step of the analysis work plan will provide the SAS logs and the outputs until the desired iterations yield satisfactory result to the investigators.

The members of the BDM Team are listed on page 15 under statistical evaluation.

# Guidelines for Publications of Manuscripts

The SCTBIFR adheres to the following principles for authorship, which are excerpted from “Guidelines on Authorship of Medical Papers” (Huth EJ. Ann Intern Med. 1986;104:269-274).

Principle 1. Each author should have participated sufficiently in the work represented by the article to take public responsibility for the content.

“Public responsibility” means that an author can defend the content of the article, including the data and other evidence and the conclusions based on them. Such ability can come only from having participated closely in the work represented by the article and in preparing the article for publication. This responsibility further requires that the author be willing to concede publicly errors of fact or interpretation discovered after publication of the article and to state reasons for errors.

Principle 2. Participation must include three steps: (1) conceptualizing or designing the work represented by the article, or analyzing and interpreting the data, or both; (2) drafting the article or revising it for critically important content; and (3) approving the final version of the article for publication.

The work represented by a scientific article includes forming the hypothesis tested by the research it reports or forming the question it answers, developing the means of gathering the reported data or other evidence, collecting data or other evidence, critically analyzing the evidence and any counter-evidence, and writing the article so that it accurately reports all of these steps and their products in the structure of critical argument.  To publicly defend an article, authors must understand thoroughly the basis for its origin (conception) and can testify to the validity of its argument (critical analysis of evidence). Furthermore, authors must have sufficient involvement in writing the article, either in drafting the initial version or revising subsequent versions to ensure validity of the argument and conclusions, to be able to defend the article as an accurate report of the work that led to it.

Principle 3. Participation solely in the collection of data (or other evidence) does not justify authorship.

Data and other evidence bearing on the conclusions and validity of a scientific article may be gathered by persons who know little or nothing of the steps critical to its main intellectual substance: the genesis, design of the work, and the critical analysis of evidence. Without this level of involvement, such persons could not take public responsibility for the main elements of an article and could testify only to the validity of elements of evidence and not to how they support the argument and its conclusion. Contributions of data by persons for whom authorship is not justified can be acknowledged.

Principle 4. Each part of the content of an article critical to its main conclusions and each step in the work that led to its publication (Principle 3: steps 1, 2, and 3) must be attributable to at least one author.  Each element of a scientific article vital to its conclusions must be publicly defensible or its validity is open to questions. Therefore, authorship must include one or more persons able to defend any of its critically vital elements.

Principle 5. Persons who contribute intellectually to an article but whose contributions do not justify authorship may be named and their contributions described—for example, “advice”, “critical review of study proposal”, “data collection”, “and participation in research”.  Such persons must give their permission to be named. Technical help must be acknowledged in a separate paragraph.

To avoid authors’ misrepresentation as being solely responsible for all that the article represents, they should indicate who provided intellectual assistance and its nature. Purely technical assistance includes collecting data, locating and abstracting literature, and work in preparing a manuscript that is not intellectual work on its scientific content.

#### III.  Program reorganization and delegation of responsibilities

The research team is reorganized to delegate specific responsibilities to the co-investigators as recommended by the SEP.  In this reorganization, individual investigators and the research associate are delegated to be in charge of six specific activities. These are: 1) Summary Data Dissemination, 2) Coordination and Planning of the EAC recommendation, 3) Operations, 4) Subproject Coordination, 5) Statistical Evaluations, and 6) Clinical Evaluations.  A revised organizational chart demonstrating these roles is included on page 16.

- Summary Data Dissemination:  Dr. Melissa McCarthy is delegated to lead the dissemination activities.  Based on policies and procedures of the Medical University of South Carolina, Office of Sponsored Research Program, regarding the participation of extramural researchers, Dr. McCarthy’s role is classified as the PI of the subcontracted activity at Johns Hopkins University.  She will oversee all activities pertaining to the dissemination of summary data to reinforce open scientific inquiry, educating the general public, and inform public policy.  Among the key summary data dissemination venues Dr. McCarthy leads is the development and periodic update of the web-based monograph.  The Webmaster and the data dissemination team consisting of the following individuals will assist her.

  - Melissa McCarthy, ScD (Team Leader)

  - Pam Ferguson, PhD

  - Wes Gravelle, MPH

  - Jak Gu, MSPH

  - 0.5 FTE Webmaster (TBD)

  - Jean Langlois, ScD (CDC Technical Advisor)

- Coordination and Planning of EAC Recommendations:  Dr. Michael Horner is the designee delegated to oversee the coordination of effort to implement the EAC recommendations including the scheduled teleconferences.  The project coordinator and database manager, Mr. Wes Gravelle, will assist Dr. Horner in this endeavor.  This activity entails identifying

Table 1. Proposed Publication Plan of the SCTBIFR Using Data from First Interview (N=2,104)

| Manuscript Title† | Purpose | Date of completion | Lead Author | Potential coauthors | Suggested Journals |
| --- | --- | --- | --- | --- | --- |
| - Operations of the SC TBI Follow-up Registry | To describe the specific functional stages of the SCTBIFR and processes involved in conducting the study. This paper is expected to supply information to states that are planning to develop a TBI registry. | 10/31/2003 | # Pickelsimer | Selassie, Gu, Langlois | Archives of Physical Medicine & Rehab. |
| - Patterns of alcohol use 1 year after TBI: A population-based, epidemiological study | To examine the patterns of alcohol use one year after TBI and assess the factors that predict heavy alcohol use. | 11/30/2003 | ##### Horner | Ferguson, Selassie, Labbate, Tweedy, Corrigan | American Journal of Psychiatry |
| - Factors associated with death after discharge | To examine the factors associated with death within 1 year after discharge with TBI and examine the causes of death. | 12/31/2003 | Selassie | McCarthy, Ferguson, | Medical Care, or Journal of Trauma |
| - The unmet service needs of people with TBI | To describe the unmet needs of people with TBI one year after discharge from acute care. | 01/31/2004 | Pickelsimer | Selassie, Veldheer, Sample, Langlois | J of Head Trauma Rehabilitation |
| - The major outcomes of TBI 1 yr. after discharge from acute care | To present the salient findings of TBI among persons who completed Yr1 interview addressing ADL/IADL and SWL. | 03/31/2004 | Selassie | Pickelsimer, McCarthy, Ferguson, Corrigan, Langlois | Journal of Trauma |
| - General Health Status 1 yr. after discharge with TBI | To evaluate the general health status and its various subscales among persons with TBI 1 yr. after discharge from acute care hospital. | 05/31/2004 | Langlois | McCarthy, Selassie Sample, Dikmen | Quality of Life Research |

A. Publications scheduled for completion from August 1, 2003 through July 31, 2004

## † Topics selected address EAC priority recommendation (Unmet needs for services, Employment, Emotional issues and secondary consequences, Cognition, ADL\IADL, Life satisfaction, and Substance abuse) in part or in full.

Table 1. Proposed Publication Plan of the SCTBIFR Using Data from First Interview (N=2,104)

| Manuscript Title† | Purpose | Date of completion | Lead Author | Potential coauthors | Suggested Journals |
| --- | --- | --- | --- | --- | --- |
| - Neurosomatic Outcomes of TBI | To identify the symptoms and neurological deficits of TBI 1 yr. after discharge from acute care hospital | TBD | Turner | Ferguson, Selassie, Gu, Guimaraes, Heinemann | Journal of Neurology |
| - Epilepsy and Seizure Disorders associated with new onset of TBI | To determine the incidence and prevalence of ESD associated with TBI 1 yr after discharge from acute care hospital. | TBD | Ferguson | Turner, Selassie, Guimaraes, Thurman | Epilepsia |
| - Early predictors of return to work | To identify the factors that are associated with return to work 1 yr. after discharge from acute care facilities with TBI. | TBD | # McCarthy | Muller, Selassie, Dikmen, Langlois | Brain Injury |
| - Cognition after TBI | To describe problems of cognition among persons discharged with TBI | TBD | McCarthy | Selassie, Corrigan, Horner, Heinemann | Journal of Head Trauma Rehabilitation |
| - Outcomes of TBI among the elderly | To describe the magnitude of adverse outcomes among the elderly and compare these outcomes with persons younger than age 65. | TBD | Selassie | Pickelsimer, Ferguson, Woods, Sample | Journal of the American Geriatrics Society |
| - Population-based TBI outcome surveillance | To describe the epidemiological paradigm and methodological uniqueness of outcome surveillance | TBD | Selassie | McCutheon, Woods, Langlois | American J of Public Health or Injury Prevention |

B. Extended list of publications planned for completion pending availability of resources and staff time

† Topics selected include EAC priority recommendation (Unmet needs for services, Employment, Emotional issues and secondary consequences, Cognition, ADL\IADL, Life satisfaction, and Substance abuse) in part or in full.

2 or 3 issues that need discussion with the EAC prior to the scheduled conference calls, preparing and sending background materials on the issues identified for discussion at least 2 weeks before the scheduled date of the conference, and presenting the progress related to the issues raised for discussion at the preceding conferences. The team members working on the coordination of the EAC recommendations are as follows.

  - Michael Horner, PhD (Team Leader)

  - Wesley Gravelle, MPH

  - Elisabeth Pickelsimer, DA

  - Anbesaw Selassie, DrPH

- Operations:  Dr. Elisabeth Pickelsimer is delegated to be in charge of project operations, which includes administrative and budgetary oversight for the program's research activities including the conduct of the targeted second and third interviews.  The Project/Data Manager, Mr. Gravelle will assist Dr. Pickelsimer by mobilizing all available and necessary resources to ensure the successful execution of the operational activities conducted at the Midland Center in Columbia.  The Midland Center houses the SC TBI Training Institute and the SCTBIFR interviewing, database, and tracking systems.  Dr. Pickelsimer will also continue to be in charge of all IRB-related activities.

- Subproject Coordination:  Dr. Pam Ferguson is delegated to be in charge of coordinating the two continuing subprojects, 1) Epilepsy with TBI, 2) the SSA assessment of SSI/SSDI assistance after TBI.  Dr. Ferguson will also oversee the conduct of relevant literature review for the development of manuscripts slated for submission.  She will be assisted by a 20-hr/week graduate assistant to develop the reference database.  For the two subproject activities, two teams are formulated.

Epilepsy with TBI Subproject Team

        - Pam Ferguson, PhD (Team Leader)

        - Robert Turner, MD

        - Jak Gu, MSPH

        - Wes Gravelle, MPH

  - Anbesaw Selassie, DrPH

SSA Subproject Team

- Pam Ferguson, PhD (Team Leader)

- Paulo Guimaraes, PhD

- Robert Turner, MD

- Mary Tyrell, MA

- Anbesaw Selassie, DrPH

- Statistical Evaluation: Dr. Paulo Guimaraes is the designee for all matters pertaining statistical evaluations.  He will be assisted by Mr. Jak Gu, Programmer and data analyst for the SCTBIFR.  Dr. Guimaraes will lead the Biostatistics and Data management Team.  The primary purpose of this team is to combine data into a single repository and customize the data for the specific research interest of the investigators and provide statistical support to the investigators.  The members of the team are as follows.

  - Paulo Guimares, PhD (Team Leader)

  - Pam Ferguson, PhD

  - Jak Gu, MSPH

  - Wes Gravelle, MPH

  - Anbesaw Selassie, DrPH

- Clinical Evaluation:  Dr. Robert Turner is the designee for all project-related clinical evaluations.  He will be mainly involved in assessing the neurosomatic outcomes of TBI for both the SSA and epilepsy subprojects.  Furthermore, he will be consulting with all investigators regarding interpretation of clinical parameters, grouping of discharge ICD-9-CM codes, developing predictive algorithms for the SSA subproject, and clustering of pre-existing conditions into meaningful categories for specific outcomes assessment.  He will also be in charge of validating the clinical evolution of TBI sustained at the time of injury.

IV.  Specific plans to implement the recommendations of the EAC

The project established a team to address the recommendations of the EAC.  The members of the team are included on page 14.  Dr. Michael Horner heads the team.  The proposed plan to address the specific recommendations is briefly described below.

- Organizational structure:

- The project developed a simplified organizational structure highlighting the tasks that are delegated.  This will be discussed with the EAC on the first conference call on November 12, 2003.  Changes will be made as deemed appropriate.

- The principal investigator delegated more responsibilities by revising what was earlier included in the noncompeting Year 2 continuation application.  This will be reported at the next conference call.

- Completion of the data codebook is scheduled for December 31, 2003.  The methods involved to achieve this objective are included under objective 7 on page 2.

- Completion of operational manual is scheduled for June 30, 2004.  This schedule is set after considering the publication priorities of the project.  The methods of completing this task along with the person delegated to oversee its completion is included on page 5 under objective 15.

- Personnel resources have been reallocated and the team formed a year ago to manage and analyze the data has now been reinforced.  Dissemination activities are delegated to Dr. McCarthy.  She will serve as the PI for subcontracted activities to Johns Hopkins University in accordance with the rules and regulations of the MUSC, Office of Sponsored Research program.

- The publication plan is updated with specific timeline and brief descriptions of the methods to be used to achieve the goal for the six manuscripts slated for completion in year 2.

- Involvement of outside experts:

  - Data dissemination plan that involves outside expertise for publication is included on pp 7-8.  The project has already included outside expertise on two of the manuscripts that are under preparation.  Further discussion with EAC will include solicitation of expert input to advance data dissemination.

- SSA substudy consultation with the University of Illinois’ Disability Research Institute:

  - The project forwarded this recommendation to Dr. Sandra Salan for her opinion.  Implementation plan will be laid out if this suggestion is amenable to SSA.

- Need for rapid dissemination of basic descriptive data:

  - A plan to rapidly disseminate basic descriptive data using the web is stated on pp 14-15, under objective 14.  Dr. McCarthy is in charge of this activity.  A workgroup that will assist Dr. McCarthy is listed on page 13 under the activity entitled ‘summary data dissemination.’  As the details of this activity unfold, progress made towards accomplishing this recommendation will be discussed with the EAC on the March 10, 2004 conference call.

- Working closely with the funding agency to determine how to maximize data dissemination:

- The principles reflecting the values of data dissemination highlighted by the EAC is included on pp 7-8.  The project adheres to these principles.  Since the inception of the study, the project has collaboratively worked with the funding agency.  The CDC Technical Advisor, Dr. Langlois, is the member of, a) the steering committee, b) the investigator’s committee, and c) the data dissemination team.  The meetings of the two committees are conducted on two separate dates each month. Every aspect of the project’s activities has been conducted with the full knowledge and participation of Dr. Langlois.  Dr. Langlois has been invited to be the lead author on the domain of general health and on a manuscript describing the operational model of SCTBIFR, which was ably spearheaded by her.  Furthermore, Dr. Langlois is listed as a coauthor on 5 other manuscripts slated for publication.  This publication plan has been in effect since November 7, 2002.  We will continue to promote genuine collaboration with CDC-NCIPC that has been the hallmark of the SC injury surveillance program since 1992.  The project will completely adhere to the following work plan to collaboratively work with the CDC.

- The project will seek CDC IRB approval until the research project is completed.  The project will not perform any activity that has not received CDC’s IRB approval.

- We will work closely to maximize the usefulness of the data, conduct the analyses, and report the findings.  This plan includes involving the CDC Technical Advisor as a lead author on at least two major topics and a co-author on at least five other manuscripts.  The CDC TA is involved in the data dissemination team in addition to the ongoing membership in the steering and investigator’s committees.

- The project will notify and invite the CDC of all conferences involving the SSA subproject.

- The project will seek the advice and counsel of the CDC on all technical and administrative issues as needed.

- The project will seek and facilitate at least one site visit during the funding period to discuss issues, resolve problems, and demonstrate progress.

- The project will seek the involvement and advice of the CDC to implement the Evaluability Assessment plan developed by Ms. Elisabeth Krause.

  - Prioritizing the topics for analysis and manuscript preparation:

- The topics prioritized by the EAC for analysis and manuscript development are very well in keeping with what the project listed in the noncompeting continuation application despite differences in the order.  The publication plan priorities suggested by the EAC will be adopted as the guideline for future manuscript preparation.  Progress on these priority areas will be discussed during the scheduled conference calls.

- Suggestions made towards presenting to the SEP:

- The committee attempted to adhere to this excellent advice during the SEP site visit.

    - Programmatic shifts and potential implications

The changes resulting from the SEP recommendation to stop the follow-up interviews by July 31, 2004 will result in higher reduction in the cumulative sample size than what was originally anticipated during the design of the study.  Persons with TBI who completed the first and second interview after July 31, 2002 and July 31, 2003 respectively will not be able to participate for the third interview.  This is because of the 9-15 months interval needed to conduct the subsequent interviews.  Furthermore, as reported in the noncompeting continuation application, the observed number of attritions for the second interviews exceeded what was originally expected. For the last 12 months, the project recorded an average of 25% attrition mainly due to failure to respond to our messages and reminders (unresponsive rate 11%, refusal 7%, deceased 5%, other 2%).  Figure 1 compares the number of first, second, and third interviews completed by July 31, 2003 with the Proposed number of interviews by July 31, 2004.

While the decision to stop the first interviews on July 31, 2003, has no significant bearing on the core project, stopping the third interview on July 31, 2004, will profoundly impact the core project’s ability to detect subgroup differences on some of the less prevalent outcomes that are analyzed as repeated measures or on some of the variables needed for adjustments in a multivariable log linear models.  Table 2 shows changes in statistical power for the various recommended sample sizes for the second and third interviews. In this example, we used the observed values for persons with TBI that reported they are unable to carry major activities of daily living (ADL) in one of the six areas.  According to our findings from the first 1,805 participants, the proportion of persons with severe TBI that are unable to carry at least one ADL is 40% higher than those with less-severe TBI.  Given these values, detecting statistically significant differences by severity diminishes to a level where the observed risk ratios, while true, could be rejected as false.  This change in sample size will impact some aspect of the data analyses that count on cumulative data.  While the representativeness of the data is well preserved, it is our strong stance that multivariable log linear modeling of the follow-up data be conducted unweighted due to the higher probability of heterogeneity between the participants and the referent population with regard to putative risk characteristics that could not be approximated from the stratification variables employed for sampling, i.e., hospital bed size and severity of TBI.

Table 1.  Changes in statistical power by proposed and recommended sample sizes

| Parameter | Proposed and recommended complete interviews |  |  |
| --- | --- | --- | --- |
| Ending dates | 07/31/2003 | 07/31/2004 | 07/31/2004 |
| Available sample size | 1st Interviews N=2,104 | 1st & 2nd Interviews N=1,575 | 1st, 2nd, 3rd Interviews N=774 |
|  | (Proposed N=2,435) | (Proposed N=1,800) | (Proposed N=1,350) |
| Level of Significance () | 0.05 | 0.05 | 0.05 |
| Test type | 2-sided | 2-sided | 2-sided |
| Severe TBIs who are unable to carry major activity in one of the six activities (2) ‡ | 12.2% | 12.2%† | 12.2%† |
| Mild TBIs who are unable to carry major activity in one of the six activities (1) ‡ | 7.2% | 7.2%† | 7.2%† |
| Desired Risk Ratio (OR) | 1.8 | 1.8 | 1.8 |
| Ratio of Severe to Mild TBI | 2:1 | 2:1 | 2:1 |
| Statistical Power (1-) | 95% | 88% | 57% |
|  | (Proposed 1-=97%) | (Proposed 1-=92%) | (Proposed 1-=82%) |

‡ Response rate from the first interviews

† Functional deficits Proposed assume constancy of the reported deficits during the period of follow-up and this information used with other dynamic state of health such as general health.

VI.   Detailed Budget Justification

Note: Spreadsheets that show separate budgets for SCTBIFR’s core project, SSA sub-project, and Epilepsy Sub-project along with the budget for the ED Surveillance project are at the end of this budget justification.

PERSONNEL—

Anbesaw Selassie, DrPH, Principal Investigator, (10% Core, 10% SSA, 20% ED TBI surveillance) is an epidemiologist and Assistant Professor in the Department of Biometry and Epidemiology at MUSC. He is responsible for the overall productivity of the project and appropriate management of the two sub studies. He directs the analyses of project data, oversees the completion of delegated tasks, and liaises with the CDC and state-based project partners. Additionally, he will participate in the dissemination activities by making presentations at meetings and writing manuscripts for publication of results in professional journals. He will consult with field experts to develop and refine the strategies of data analysis and interpretation.  Dr. Selassie is also the PI for the ED TBI surveillance program.

Elisabeth Pickelsimer, DA, Co-Investigator, (30 % Core) is a Research Assistant Professor of the Medical University of South Carolina, Department of Biometry and Epidemiology. She is responsible for the operational activities of SCTBIFR including oversight of administrative and budgetary activities.  She has been leading the project’s effort on developing the survey tool, aiding the interviewers as problems occur, evaluating the quality of data acquired through interview, writing IRB protocols, generating and disseminates sub-contracts, developing budgets, participating in writing reports and manuscripts.  Dr. Pickelsimer serves as a member of the SCTBIFR Steering Committee and will supervise the project coordinator/database manager.

Michael Horner, PhD., Co-Investigator, (10% Core), is an Assistant Professor of the Medical University of South Carolina, Department of Psychiatry. He will participate in the interpretation and analysis of SCTBIFR data, particularly in the interpretation of variables related to cognition and substance abuse. In addition, Dr Horner will participate in manuscript writing and will have responsibility for the organization of the scheduled conference calls with the External Advisory Committee and the CDC.

Robert Turner, MD, Co-Investigator/Epileptologist, (5% Epilepsy, 10% SSA), is an Assistant Professor of the Medical University of South Carolina, Department of Neurology. He serves as the clinical evaluator for the epilepsy subproject and social security components of the project. In addition, he will participate in manuscript writing, in particular on the topic neuro-somatic sequelae of traumatic brain injury.

Paulo Guimaraes, Ph.D., Co-Investigator, (10% Core, 10% SSA) is a statistician and Assistant Professor in the Medical University of South Carolina, Department of Biometry and Epidemiology. He serves as the occupant statistical expert and advisor and provides ongoing consultation, analyses, and advice on analytic approaches, weighting of sampled observations, economic modeling, and censoring of data. Dr Guimaraes will lead the Biostatitistics and Data Management team.

Pamela Ferguson, PhD, Research Associate, (20% SSA, 10% Epilepsy), is a Research Associate at the Medical University of South Carolina, Department of Biometry and Epidemiology.  Dr Ferguson will be responsible for coordinating the two subprojects, managing the literature reviews, participating in data analysis, and manuscript preparation..

Wes Gravelle, MPH, Project Coordinator/Database Manager,  (48% Core, 52% ED TBI), helps manage the day-to-day operations of the SCTBIFR at the Midlands Office. His responsibilities include personnel oversight, writing reports for the Steering Committee and the CDC, participating on state committees relative to TBI services and prevention, and providing liaison with other state agencies. Furthermore, Mr. Gravelle has responsibility for the data entry platform, data acquisition, quality assurance, analysis, report generation, and sharing of summary and case level data with CDC.  Mr. Gravelle also serves as the Project Coordinator for ED TBI Surveillance project.

Jakook Gu, MSPH, Programmer/Statistician, (30% Core,5% Epilepsy, 65% ED TBI). Mr. Gu’s primary responsibilities are programming of statistical and data collection applications—primarily SAS and Epi Info. He also participates in data processing, including merging and collating data to the specification of the CDC guidelines, quality assurance, analysis, report generation, and sharing of summary and case level ED TBI surveillance data with CDC.

Sally Broadhurst, MS, OTR, Interviewer, (50% Core), is responsible for advising PRN interviewers, interviewing participants and providing quality assurance.  In addition, she is responsible for collecting and editing follow-up data and for developing materials and providing training of new interviewers.

Timothy Hickman, BS, Interviewer, (100% Core), is responsible for tracking and interviewing participants, including prisoners, collecting and editing follow-up data, and ensuring the completeness of the information acquired through telephone survey.

Robin Butler, BS, Interviewer, (50% Core), is responsible for tracking and interviewing participants, including prisoners, collecting and editing follow-up data, and ensuring the completeness of the information acquired through telephone survey.

PRN, Interviewer, (50% Core), is responsible for tracking and interviewing participants, collecting and editing follow-up data, and ensuring the completeness of the information acquired through telephone survey.

Terri Dashiell, Administrative Assistant, (45% Core), will assist with day-to-day project activities, such as procurement and processing travel and participant reimbursements.

TBN Bioinformatics PhD Student, (20 hr week Core), will help develop and maintain the project’s web-based dissemination activities as suggested by the EAC. Of note, graduate students are not permitted to work over 20 hours per week. Therefore, 1.0 FTE equals 20 hours.

TBN PhD Student, (16 hr week Core), will assist with literature reviews for proposed manuscripts. Of note, graduate students are not permitted to work over 20 hours per week. Therefore, .80 FTE equals 16 hours.

Fringe Benefits are calculated at the federal approved rate of 26.6%.

# TRAVEL

- Several SCTBIFR key personnel (Drs Selassie, Pickelsimer, Guimaraes, Horner, and Turner) are faculty members of the Medical University of South Carolina in Charleston. Many project activities take place in Columbia, 120 miles from Charleston. For example: the SCTBIFR Steering Committee and the Abstraction Committee meet monthly; the SC TBI Leadership Council meets quarterly and is attended by SCTBIFR project personnel where they often present project findings. Additionally, the SCTBIFR staff work in facilities provided by DDSN in Columbia where the monthly Injury Team, comprised of all staff and Drs Selassie and Pickelsimer, meets. Furthermore, members of the SCTBIFR project team frequently travel between Columbia and Charleston to work with Dr Selassie. And, when the CDC conducts site visits, we heretofore have traveled to both cities. Therefore, funding for in-state travel (Charleston to Columbia or Columbia to Charleston) is calculated at 240 miles roundtrip @ .345 mile, $32 per diem x 2 persons, (12 trips $1,162, Core), (4 trips $339, SSA), (3 trips $312 Epilepsy), (10 trips ED, $723).

- Attendance at the Grantees’ meeting in Atlanta is requested. This is estimated at 3 persons, 3 days, accommodations, transportation, per diem ($1,262 ED).

- Out-of-state travel to attend out-of-state conferences for dissemination of project findings is estimated at 2 persons, 3-4 nights’ accommodations, registration fee, transportation, shuttle, airport parking ($1,823 Core; $2,226 ED).

- In-state travel to attend the state Brain Injury and/or the SC Public Health Association conferences is estimated at 2 persons, 2 nights, transportation, registration fee, per diem ($550 Core, $832 ED).

- Drs Selassie and Guimaraes will travel to Bethesda on Oct 20-21 for a two-day meeting with SSA. Funding for travel is calculated at 2 persons, 2 nights’ accommodations, transportation, shuttle, airport parking ($1,472 SSA).

# SUPPLIES

- Based on previous years of conducting this project, supplies for subject correspondence (introductory letter, Business Reply envelopes, consent, tracking, subject reimbursements, thank you) are estimated at $2.50 per participant ($2,003 Core).

- General supplies are estimated ($695 Core, $318 Epilepsy, $275 SSA, $350 ED).

- Educational materials, such as revised SF-36 Scoring Manual and other documentation on methodology of scoring the instruments included in the questionnaire, are estimated ($526 Core).

- Materials for publication development (copying of articles, requests for article not available in the MUSC library, etc., are estimated ($805 Core, $492 ED).

# OTHER

- Participant introductory letter monetary incentives at $1 per letter for all interviews are calculated as follows: Second interview (500 letters), Third interview (698 letters) for a total ($1,198 Core).

- Based on the attrition rate during our three years of conducting interviews, participant remunerations are calculated at $15 per participant as follows: Year 2 interview (352 participants), Year 3 interview (449 participants) ($12,015 Core).

- Based on previous charges, Internet service for 5.5 staff in the Midlands office is calculated at $20 per month, per person ($1,320 Core).

- Based on previous costs, toll-free number service for potential participants to make inquiries is approximated ($630 Core).

- Interviewer calling cards for our PRN interviewers and those who have scheduled off-hour interviews, for example 6 am, are estimated ($1,177 Core).

- Software and site licenses are calculated as follows (1 ref manager @ $300, 1 SUDAAN w/SAS @$359, 2 renewals @ $125, MetroSearch @ $562, Adobe Acrobat $495 ($1,911 Core); 2 SAS renewals @$100 ea, 1 Ref Manager @$300 ($500 ED). Of note, MUSC allows us a 26% F & A because the majority of employees are housed at the Midlands office in Columbia. They are therefore not part of the IT network provided at MUSC. Due to the decreased F & A, the project is required to purchase all software and licenses for the Midlands office.

- Cell phone service is calculated at $40 per month ($480 Core). Dr Selassie uses this phone so that project staff can contact him.

- We have at least one site visit per year. It meets in Columbia and Charleston. Food for this meeting is requested ([2] working meals per day is calculated at $7 breakfast and $10 lunch for 20 persons) ($680 Core).

# CONSULTANTS

- Accessible Data   hour will continue to provide expertise in maintaining and revising the computerized interview database and will help with our proposed web page for dissemination of project findings. This is calculated at $80 x 20 hours ($800 Core).

- Ernest McCutcheon, MD, MPH, will continue to serve as SCTBIFR technical adviser.  In addition to serving on the Steering Committee, he will help interpret findings and follow-up reports, present study results, edit reports and manuscripts, and represent the project at specified meetings. This is calculated at $50 hour x 60 hours ($3,000 Core).

MUSC’s F & A costs are calculated at the Modified Total Direct off-site rate of 26%. They include F & A costs applied only to the first $25,000 of each subcontract.

##### FACILITIES AND ADMINISTRATION COSTS

# CONTRACTUAL

  - South Carolina Department of Health and Environmental Control (DHEC)

Medical Record Abstraction

Assistant Project Coordinator (20% Epilepsy, 30% ED) will supervise the part-time data abstractors, make their assignments, and will have personal responsibility for the review of hospital medical records. This individual also will perform re-abstraction to ensure the quality of data collected and will conduct a second review of the medical records of those persons who reported epilepsy or seizure disorders.

Upstate DA (45% ED) will be responsible for reviewing 1,100 medical records. (ED)

Part-time medical record abstractors will review 2,000 ED records at $3 per record. (ED)

Fringe Benefits are calculated at the agency rate of 30% for FTEs and 10% for part-time abstractors.

- Mileage: Abstractors will be reimbursed for travel to all hospitals where participants were hospitalized and to meetings and training activities. Reimbursement for their travel is calculated at the state rate of $ .345 per mile. Lodging: Overnight lodging is warranted when a large number of abstractions are needed in a geographical area that is located in the corners of the state. Therefore lodging is calculated at $69 per night, $25 per diem x 10 nights. For mileage and lodging we estimate ($2,000 ED).

- Out-of-state travel, perhaps a grantees’ meeting in Atlanta is calculated @$1,000 for 2 persons to attend.

- Abstraction tools, manuals, and disks are estimated ($250 ED).

Health Services Support:  Due to reorganization within the Health Services deputy area of the DHEC, new methods have been devised to minimize the expense of processing expenditures provided for the general benefit of all programs. These types of expenditures are eligible for direct charge to federal programs. Each program is assessed its fare share to pay for these expenses on specific cost principles. This is calculated @7.68% of salary.

F & A Costs

DHEC’s F & A cost rate is applied to personnel at the federal approved rate of 12.3%. ($2,497 ED)

  - South Carolina Department of Disabilities and Special Needs (DDSN)

Attendance at one national conference ($2,000) related to brain injury for Dr. Linda Veldheer, Director of the Head and Spinal Cord Injury Division and site administrator of the Columbia site.

- DDSN provides free office space in Columbia for the SCTBIFR project/data manager, four interviewers, and a statistician/data analyst. Recruitment materials and participation thank you letters are prepared at the Columbia site and mailed through the DDSN postal system. Postage for these mailings is requested at $1,500.

- General phone service for 5.5 SCTBIFR team members is estimated at $140 month.

- The cost of a headset and telephone for the TBN interviewer is calculated at $320.

- Funding for long-distance phone charges (1,666 expected interviews x 60 minutes/ea x $ .05/min + phone charges for tracking and scheduling of interviews) is requested at $6,000.

DDSN’s F & A rate is applied at 1.92%.

The total amount of the contract is $12, 740 (Core).

C.	Office of Research and Statistics (ORS) of the State Budget and Control Board

ORS will supply the necessary statistical and health services research services to link the Social Security Administration information with the in-state healthcare utilization databases, inpatient hospitalizations, emergency room data, and ambulatory surgery data.  This will be a service rendered contract with all costs associated with the project paid by SCTBIFR. Payment to ORS will be based on deliverables specified in the contract for the project. The contract includes staff time for programming, cleaning the various data sets, statistical analyses, costs associated with obtaining data sets from other agencies, other resources useful for the completion of the project, and for 2 persons to travel to Bethesda for two weeks to work with SSA. The contract has been calculated as follows:

Personnel at 25% FTE

Ms Mary Tyrell, Administrator @ .05 FTE

Fringe at 30.5%

Supplies: General Office ($200)

Travel: project meetings ($ .345 mile x 720 miles, $32 per diem, 2 persons= $440); Bethesda (12 days: accommodations, per diem, airfare, shuttle [$3,158].

Other: CPU time at 10% of salary; SAS licenses at $200; Telephone ($30 month— $360)

Tracking processes: ORS will try to determine if participants in the SCTBIFR who have been lost to follow-up can be located from other statewide datasets. ($3,000)

The total amount of the contract is $30,000 SSA.

- Johns Hopkins University, Department of Emergency Medicine

Melissa McCarthy, MPH, ScD: Under this contract, Dr. McCarthy will serve as the PI of the data dissemination activities subcontracted to Johns Hopkins University and will provide input and feedback regarding data interpretation, standardization, and manuscript development as well as work closely with the PI and co-investigators regarding ongoing data dissemination activities and the productivity of manuscript development.  Dr McCarthy will lead the development of the web-based monograph and will assist in the development of the data codebook and the manual of operations.  It is expected that at least two manuscripts will be submitted during the funding period with Dr. McCarthy’s involvement as the lead author or co-author. The contract is calculated as follows: 20% FTE; fringe benefits at 29%, facilities and administration costs at 63.5%. The total amount of the contract is $29,337 Core.